## Phillip
To-do list
To be completed by: |  |  |  | Name Phillip Charles
Deadline: |  |  |  | Date 11-20-2022
Project 3
% done | Phase | Start By | Original Due By | Revised Due By | Number Of Days | Revision Notes
100% | Meeting 1 Planning | 2022-11-20 | 2022-11-20
100% | Data Modeling | 2022-11-20 | 2022-11-27 | 2022-12-08 |  | Eliminate many to many relationships in CDM with bridge tables
100% | DbSecurity and TrackWorkflow | 2022-11-20 | 2022-11-27
100% | Meeting 2 Planning | 2022-11-27 | 2022-11-27 | 2022-12-04 |  | Replaced with group updates given curremt progress and other class standing.
100% | Assigned Procedures | 2022-11-20 | 2022-11-27
100% | Code aggregation, revision, testing | 2022-11-27 | 2022-12-04
0% | Propositions | 2022-12-04 | 2022-12-08
0% | JDBC Setup | 2022-11-27 | 2022-12-04
0% | Group 02 Videos | 2022-12-08 | 12/10/202
0% | JDBC Video | 2022-12-08 | 12/10/202

## Jasmine
To-do list
To be completed by: |  |  |  | Name
Deadline: |  |  |  | Date
Project 3
% done | Phase | Start By | Original Due By | Revised Due By | Number Of Days | Revision Notes
100% | Assigned Procedures | 2022-11-20 | 2022-11-27 | 2022-12-04 |  | Extension given curremt progress and other class standing.
100% | Assigned Tables | 2022-11-20 | 2022-11-27 | 2022-12-04 |  | Extension given curremt progress and other class standing.
100% | Add/Drop Foreign Keys | 2022-11-20 | 2022-11-27
100% | Data Modeling | 2022-11-20 | 2022-11-27 | 2022-12-08 |  | Eliminate many to many relationships in CDM with bridge tables
100% | Propositions | 2022-12-04 | 2022-12-08
0% | Group 02 Videos | 2022-12-08 | 12/10/202
0% | JDBC Video | 2022-12-08 | 12/10/202

## Ryan
To-do list
To be completed by: |  |  |  | Name
Deadline: |  |  |  | Date
Project 3
% done | Phase | Start By | Original Due By | Revised Due By | Number Of Days | Revision Notes
100% | Assigned Procedures | 2022-11-20 | 2022-11-27 | 2022-12-04 |  | Extension given curremt progress and other class standing.
100% | Assigned Tables | 2022-11-20 | 2022-11-27 | 2022-12-04 |  | Extension given curremt progress and other class standing.
100% | Project Tracking | 2022-11-20 | 2022-11-27 | 2022-12-06 |  | Delay caused by other classes and time delegation.
100% | Propositions | 2022-12-04 | 2022-12-08
100% | JDBC Setup | 2022-11-27 | 2022-12-04
100% | Group 02 Videos | 2022-12-08 | 12/10/202
99% | JDBC Video | 2022-12-08 | 12/10/202

## Sean
To-do list
To be completed by: |  |  |  | Name
Deadline: |  |  |  | Date
Project 3
% done | Phase | Start By | Original Due By2 | Revised Due By | Number Of Days | Revision Notes
100% | Assigned Procedures | 2022-11-20 | 2022-11-27 | 2022-12-04 |  | Extension given curremt progress and other class standing.
100% | Assigned Tables | 2022-11-20 | 2022-11-27 | 2022-12-04 |  | Extension given curremt progress and other class standing.
0% | Propositions | 2022-12-04 | 2022-12-08
0% | JDBC Setup | 2022-11-27 | 2022-12-04
0% | Group 02 Videos | 2022-12-08 | 12/10/202
0% | JDBC Video | 2022-12-08 | 12/10/202

## Oliver
To-do list
To be completed by: |  |  |  | Name
Deadline: |  |  |  | Date
Project 3
% done | Phase | Start By | Original Due By | Revised Due By | Number Of Days | Revision Notes
100% | Assigned Procedures | 2022-11-20 | 2022-11-27 | 2022-12-04 |  | Extension given curremt progress and other class standing.
100% | Assigned Tables | 2022-11-20 | 2022-11-27 | 2022-12-04 |  | Extension given curremt progress and other class standing.
0% | Propositions | 2022-12-04 | 2022-12-08
0% | JDBC Setup | 2022-11-27 | 2022-12-04
0% | Group 02 Videos | 2022-12-08 | 12/10/202
0% | JDBC Video | 2022-12-08 | 12/10/202

## Samiha
To-do list
To be completed by: |  |  |  | Name
Deadline: |  |  |  | Date
Project 3
% done | Phase | Start By | Original Due By | Revised Due By | Number Of Days | Revision Notes
100% | Assigned Procedures | 2022-11-20 | 2022-11-27 | 2022-12-04 |  | Extension given curremt progress and other class standing.
100% | Assigned Tables | 2022-11-20 | 2022-11-27 | 2022-12-04 |  | Extension given curremt progress and other class standing.
0% | Propositions | 2022-12-04 | 2022-12-08
0% | JDBC Setup | 2022-11-27 | 2022-12-04
0% | Group 02 Videos | 2022-12-08 | 12/10/202
0% | JDBC Video | 2022-12-08 | 12/10/202